## Knight+Player
Category | Asset | Not Started/Assigned To | In progress | Committed | Implemented | Sign-Off
Knight / Player
Sprites | body | cam/lydia |  | x | x
| legs | cam/lydia |  | x | x
| helmet | cam/lydia |  | x | x
Sword
|  |  |  | x | x
foreground | purple circle flower | cam/lydia |  | x | x
| yellow tall flower | cam/lydia |  | x | x
| grass | cam/lydia |  | x | x
| light bush | cam/lydia | x
| dark bush | cam/lydia | x
| 4 leaf tree | cam/lydia |  | x
| blue flower | cam/lydia |  | x | x
| wagon | cam/lydia |  | x | x
| middle green bush | cam/lydia | x
| 3 leaf tree | cam/lydia |  | x | x
| short 3 leaf tree | cam/lydia |  | x | x
| red box flower | cam/lydia |  | x | x
| 4 leaf tree #2 | cam/lydia |  | x | x
| windmill (not door) | cam/lydia |  | x | x
| double yellow flower | cam/lydia |  | x | x
background
| sky | cam/lydia |  | x | x
| cloud 1 | cam/lydia |  | x | x
| cloud 2 | cam/lydia | x
| dark mountains | cam/lydia | x
| light mountains | cam/lydia | x
| cloud 3 | cam/lydia | x
| cloud 4 | cam/lydia | x
| darkest mountains | cam/lydia | x
interactive objects
| dummy | liam |  | x | x
| fly | liam |  | x | x
| fly wings | liam | x
| door | liam |  | x | x
Script | script scene change | liam |  | x | x
| Script health | liam |  | x | x
| fly side to side | liam |  | x | x
| fly circle | liam | x
| fly up and down | liam |  | x | x
Sound | Sound hit | tommy |  | x
| sound death | tommy |  | x
| music | tommy |  | x
Prefabs | fly | liam |  | x | x
| flower colors | liam |  | x | x
start screen | grass | liam | x
| title | liam |  | x | x
| background | liam |  | x | x
| fly | liam |  | x | x
| flypath | liam |  | x | x
| red flower | liam | x
| purple flower | liam | x
| yellow flower | liam | x
| blue flower | liam | x
| tall yellow flower | liam | x
| fly particles | liam | x |  | x
| start button | liam |  | x | x
| noise when click on button | tommy |  | x
| music | tommy |  | x
die screen
| background | liam |  | x | x
| game over | liam |  | x | x
| button | liam |  | x | x
| music | tommy |  | x
| noise when click button | tommy |  | x
win screen
| background | liam |  | x | x
| the end text | liam |  | x | x
| button replay | liam |  | x | x
| music | tommy |  | x
| noise when click button | tommy |  | x